## Slide 1
Master Academic Plan Update
10/18/19

## Slide 2: BSU Strategic Plan, 2018-23 A Plan Built on Anticipated Enrollment Growth
Bemidji State University
Academic and Student Affairs Meeting 8/20/19

## Slide 3: Reflections on 2018 ASA Presentation, 8/21/18
Master Academic Plan, 2018-23 Sources of Direction and Inspiration
BSU Strategic Plan
Provost and VPASA’s Priorities
Ideas of the MAP Committee’s Twenty-One Members

## Slide 4: The Five Priority Statements
Strengthen Curriculum and Assessment Practices (for programs, departments, and Liberal Education)
Infuse Themes of Place and Fundamental Values throughout the Curriculum and Learning Experiences
Increase Diversity and Depth to which Diversity is Understood, Honored, and Celebrated through Academic and Other Learning Experiences
Increase the Positive Impact of Interactions among Students, Faculty, and Staff in All Aspects of the Learning Experience
Increase and Strengthen BSU’s Degree Program Offerings, Activities, and Events to Expand Learning Opportunities

## Slide 5: Gold = Accomplished Green = Where We’re Supposed to Be But Ongoing Burnt Orange = Not Yet Where We’re Supposed to Be
The Color Code

## Slide 6
MAP Activities | 2018-19 | Progress Update | 2019-20 | Progress Update
Priority 1 Activities | Shared Fundamental Values Task Force Assessment Pilot | Pilot Assessment Complete and Measure Added to Review | Shared Fundamental Values Task Force Assessment Tool Finished | Assessment Committee will Gather Feedback and Refine Measure for 2020-21
Strengthen Curriculum and Assessment Practices | Assessment Cmt. & Liberal Ed. Cmt. Develops Standards & Practices for Incorporating Shared Fundamental Values into the Lib. Ed. Curriculum | Standards & Practices Established and Published | Liberal Education Committee Implements Use of Shared Fundamental Values Assessment Tool | Liberal Education Committee will Gather Feedback and Refine Tool for 2020-21
 | Liberal Ed. Task Force Develops Comprehensive Learning Outcome & Name Proposal | Comprehensive Learning Outcome & Name Proposed and Approved | Liberal Ed. Task Force Reviews Current Lib. Ed. Program through Lens of CLO & Name | Liberal Education Task Force will Conduct Review and Propose Next Step by April 1

## Slide 7
MAP Activities | 2018-19 | Progress Update | 2019-20 | Progress Update
Priority 2 Activities | BSU Conversation on Honoring American Indian Connections to Place | AIRC Director Led Conversation with Tribal Leaders on 6/25/19 | Teaching & Learning Center, Academic Affairs, and Marketing & Com-munications Collabor- ation on "Place" & SFV Awareness & Interdepart- mental Relationships Plan | Teaching & Learning Center, Academic Affairs, and Marketing & Communications will Develop Plan for Review by April 15
Infuse Themes of Place and Fundamental Values |  |  | Assessment Committee Leads Collaboration on Evaluation of "Place" Incorporation | Assessment Committee Will Follow SFV Model to Complete "Place" Evaluation Measure by May 1.
 |  |  | Community Engagement Council & American Indian Communities Complete Assess. of Student Opportunities in American Indian Nations & Communities | Community Engagement Council & American Indian Resource Center will Complete and Publish Opportunities Assessment by 5/1

## Slide 8
MAP Activities | 2018-19 | Progress Update | 2019-20 | Progress Update
Priority 3 Activities | Community Engagement Council, Director of AIRC & Indigenous Studies Faculty Decide on Combining Indigenous Knowledge Listen. Sessions with Student Opps. | Decision Made to Combine Indigenous Knowledge & Student Opportunities Sessions into 6/25/19 Meeting | Agreed Upon Group Conducts Indigenous Knowledge Listening Sessions | Community Engagement Council & American Indian Resource Center will Consider whether Follow-up Sessions are Needed by 1/1
Increase Diversity and Depth to which Diversity is Understood, Honored, and Celebrated | Provost Completes Reorganization of the International Program Center to Focus on Recruiting | IPC Reorganization Complete & Implemented | Academic Affairs, Director of the American Indian Resource Center, Director of Sustainability Office, and Indigenous Studies Faculty Begin Work on Interdepartmental Relationships & Create Website | Academic Affairs, Director of AIRC, Director of Sustainability Office, will Prepare Plan & Oversee Website Creation by 6/1
 | Provost's Council, Teaching & Learning Center, Center for Diversity, Equity & Inclusion, & International Program Center Host Workshop on Incorporation of International Scholars Programs & CDEI Events into Curriculum | Preliminary Conversations Begun Informally, but Workshop Not Held; will Complete by 3/15 | Community Engagement Council Considers Sponsoring Lecture Series | Community Engagement Council will Reach Decision and Submit Proposal to Provost by 3/1

## Slide 9
MAP Activities | 2018-19 | Progress Update | 2019-20 | Progress Update
Priority 3 Activities | New Director of International Program Center Hired | Director Hired & Began Work 1/9/19 | Academic Affairs, Teaching & Learning Center, & Student Life Begin Collaborate on Events Calendar Linked to SLOs | Academic Affairs, Teaching & Learning Center, & Student Life will Develop SLO Calendar for Implementation in Fall '20
Increase Diversity and Depth to which Diversity is Understood, Honored, and Celebrated | Academic Affairs, Liberal Education Committee, & Enrollment Management Consider Short-term Goal Area 8 Options | Decided to Let Goal Area 8 Options (Global Perspective) Develop Organically & Review |  | 
 | Academic Affairs Begins Exploring Addition of New Language Options | Added German in 2018-19; considering other languages (e.g. French, Mandarin) |  | 

## Slide 10
MAP Activities | 2018-19 | Progress Update | 2019-20 | Progress Update
Priority 4 Activities | Student Life & Enrollment Management Collaborate with Faculty in Considering Changes to BSU 101 | Decided on Changes and Implemented Fall 2019 | Academic Affairs & Enrollement Begin "Best Practices" Advising Series | First Event in Ongoing Series Planned for Spring 2020
Increase the Positive Interactions among Students, Faculty, and Staff | Student Life & Center for Professional Development Begin Fall Startup Event | Event Launched Fall 2018 and Continued Fall 2019 | Deans & Chairs Begin Onboarding/Mentoring Program | Deans & Chairs Will Complete Design for Fall 2020 Implementation by 7/1
 | Academic Affairs & Enrollment Management Pilot "Best Practices" Advising Workshop | Pilot Workshops Held in Fall & Spring 2018-19 | Academic Affairs Decides whether to Continue Sponsoring Gardner Institute- Gateways Participation | Determined to Continue Attending GI Events but Discontinue Membership

## Slide 11
MAP Activities | 2018-19 | Progress Update | 2019-20 | Progress Update
Priority 4 Activities | Deans and Chairs Collaborate to Create Onboarding/ Mentoring Program | Human Resources Took Point in 2018-19; Deans Beginning to Engage Chairs for 2019-20 | Academic Affairs & Enrollment Management Host Advising Conversations & Propose Revision to Advising Prog. | Conversations, in Collaboration with CPD, Will Take Place Spring 2020
Increase the Positive Interactions among Students, Faculty, and Staff | Deans & Chairs Develop & Propose Plan for Departmental Talks | Initial Discussion Suggested that Sufficient Level of Talks Generally in Place | Deans & Departments Implement Approved Plan for Department Talks | Deans and Departments Will Develop Plan for Better Coordinating Event Schedules by 2/1
 | Director of International Recruiting and International Program Center & IPC Staff Consider How to Expand Fac./Staff Participation In Recruiting | More Faculty & Staff Visiting International Universities; IPC Engaging More Faculty & Staff in Recruiting | Provost's Council Considers Creation of Open Schedule Block | Provost's Council Determined Not to Implement Creation of Open Schedule Block

## Slide 12
MAP Activities | 2018-19 | Progress Update | 2019-20 | Progress Update
Priority 4 Activities | Director of International Recruiting and International Program Center & IPC Staff Consider How to Increase Host Families | IPC Expanding/Revising Host Concept to Include Summer Groups & Visiting Faculty | Provost's Council Considers Employee Incentive Structure for Diversity & Inclusion Events | Provost's Council Determined to Permit Staff Participation in Diversity & Inclusion Events During Workday for All Academic Affairs & Student Life Areas
Increase the Positive Interactions among Students, Faculty, and Staff | Director of International Recruiting and International Program Center & IPC Staff Consider How to Continue Expanding International Scholars Programs | Coordinator of NorthStar Program Made Full-time, and Programs Expanded | Center for Professional Development Considers Incorporation of "Creating Self-Regulated Learners" into Program for Fall 2019 Startup | Center for Professional Development Elected Not to Include CSRL into Fall 2019 Program; May Do So Later
 | Student Life and Enrollment Management Begin Full Student Retention Initiative | Student Success Council Expanded in Size and Focus |  | 

## Slide 13
MAP Activities | 2018-19 | Progress Update | 2019-20 | Progress Update
Priority 5 Activities | Academic Affairs & Marketing & Communications Begin Collaborating on Marketing Programs & Events, Especially in Liberal Arts | Collaboration begun Fall 2018 and Continues to be Refined | Academic Affairs Considers Adding Competency-based Models to Provost's Council Retreat | Competency-based Models on Provost's Not Placed Council Agenda for 2019-20; Will Wait to See What Unfolds at System Level
Increase and Strengthen BSU's Degree Program Offerings, Activities, and Events | Academic Affairs and Enrollment Management Continue Collaboration on Articulations | Both Domestic and International Articulations Continue Expanding at a Significant Rate | Academic Affairs Consider Adding Bridge Programs., etc. | Creating First Micro-Credential Badge for 2020 Implementation; Launching ESL Pathway Program; Will Continue Exploring Options
 | Academic Affairs & Enrollment Management Continue Collaborating On Expanding Existing Programs for Unmet Need | Both Undergraduate and Graduate Programs Continue Expanding | Provost & CFO Consider How to Encourage Cross-disciplinary Learning | Provost and CFO Will Complete Consideration of Cross-disciplinary Model by 4/1

## Slide 14
MAP Activities | 2018-19 | Progress Update | 2019-20 | Progress Update
Priority 5 Activities | Provost's Council Distributes Market Research One-Pager | One-pager Developed and Distributed with New Revenue-sharing Model; Additional Advice Being Developed | Academic Deans Council Explores Ways to Encourage Attendance at Honors & Other Events | Academic Deans Council Continuing to Explore Ways of Better Encouraging Event Attendance
Increase and Strengthen BSU's Degree Program Offerings, Activities, and Events | Grant-writer Hired | Grants Specialist Hired and Began Work 1/9/19 |  | 
 | Provost Presents Revised Revenue-sharing Model for Approval | Revenue-sharing Model Presented and Approved. |  |