|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **Task** | **Map Reference** | **Timeline** | **Responsible Party(ies)** | **Status** |
| Student Career Placement | II.2.3.5 | Fall, 2013 | Career Services | Added internship coordinator spring 2013. Services are available for all who graduate from BSU. Secured 20 slots for students to work in China and are hoping to move those to internships. |
| Global Learning Classroom(s) | II.3.1.1c | Fall, 2013 | Provost, VP IEL,  Director of International Relations | Installed fall 2013 and is operational. Pursuing grant with Tribal Consortium partners for securing same at tribal college sites. |
| Administrator Evaluation Process | II.4.8 | Fall, 2013 | Deans' Council, Provost | Updating in progress to modify from spring 2013. Leadership survey which will be used to develop new evaluative survey has been distributed. |
| Move beyond NTC/BSU alignment | II.4.11 | Fall, 2013 | Reinvention task force. | Reinvention taskforce appointed with April deadline to submit a reinvention plan for NTC. |
| Assessment of Student Learning | II.2.5.1 | Fall, 2013 and Ongoing | Assoc. VP Acad. Affairs, Academic Assessment Committee | In process. All departments but one current. |
| Focus on Student Advising | II.2.5.2 | Fall, 2013 and Ongoing | Deans' Council, VP SDE | To be addressed. Initial conversation between AA and SDE have occurred. We are looking at what other universities have done to connect advising to the improvement of student retention. Have pushed for use of EARS among faculty. |
| Interdisciplinarity in faculty searches | II.2.3.8 | Fall, 2014 and Ongoing | Deans' Council | All PD’s are being reviewed for this. Departments are encouraged to consider creation of interdisciplinary positions and programs. Developing a written statement for campus regarding course prefixes and funding. |
| Curriculum interdisciplinarity | II.2.3.8 | Fall, 2014 and Ongoing | Deans' Council, Curriculum Committee, Faculty Senate | Renewed course redesign grant with emphasis placed on interdisciplinarity. Funds are available for course redesign around this topic. Liberal education committee charge to create distinctiveness could also impact thinking in this area. |
| Dual Enrollment for International Students | II.3.1.3 | Fall, 2014 and Ongoing | Academic Affairs, Admissions, Records, Provost, Director of International Relations | Working with AASCU/CEAIE staff on 1-2-1 programming. Signed agreement with WSU to create an Intensive English Center at BSU that will open in July 2014. Virgil Bakken gathering departmental interest in participating in 1-2-1 programming. |
| Distinctive Liberal Education Experience | II.2.3.1 | Fall, 2015 and Ongoing | Liberal Education Committee, Deans' Council | Liberal education committee meetings are in progress. Draft process has been distributed. Work will continue this spring. |
| Communication across the curriculum | II.2.3.3 | Fall, 2015 and Ongoing | Liberal Education Committee, Deans' Council | To be addressed. |
| Enhanced Summer Residential Experience | II.2.2.3 | Fall, 2017 and Ongoing | Angie Gora | Greatly increased summer camp and summer programming in 2013. Expanding for summer 2014. Summer schedules in place through 2018. Just linked to two universities in China wishing to send students and faculty to BSU for summer workshops. |
| Mission, Vision, Values, and Introduction | I, II | Life of the Plan | Deans' Council, Campus as a whole | Added mission, vision, values statements to all AA meeting agendas. Posted same on AA website. |
| Program review- financial sustainability indicators | II.1.1.4 | Ongoing | Deans' Council | Completed for fall 2013. |
| Partnerships | II.1.2.3 | Ongoing | Deans, VP IEL | Tribal consortium, NW consortium, Greater Bemidji, Bemidji LEADS, Bemidji Roadmap, Watermark Art Center, CIBT partnership universities, AASCU/CEAIE all active and we are represented at all. Received $500K grant to link tribal colleges and BSU together using audio/videoconferencing high def web-based technology. |
| Recognize exemplary service | II.1.4.2 | Ongoing | Deans' Council, Cabinet | Planning for this in process. Will be on deans’ council agenda in March. Suggesting alumni hall of fame or similar. |
| Serving diverse populations | II.2.3.4a | Ongoing | Affirmative Action Officer, Deans' Council, Admissions, AVPAA | Working on revised hiring process and new checklist. AA officer engaged in this with HR. Partnerships listed above to help provide diversity in student population. |
| Multicultural learning community | II.2.3.4b | Ongoing | Deans' Council, AVPAA | Working to diversify campus. Climate survey completed in spring 2013. Safe place identified for LGBT students. Multicultural Center and staffing in planning process through SDE. |
| University focus on sustainability | II.2.3.9 | Ongoing | Vice Presidents | Need to have a conversation about how to incorporate this into the curriculum to a greater extent. |
| Engage Bemidji community in internationalization efforts | II.3.2.3 | Ongoing | Academic Affairs, VP IEL, Director of International Relations | Summer camp for middle/high school international students summer 2013 is renewed for 2014 and we expect 40-50 students. Met with three civic groups: Sunshine Rotary, BemidjiLeads and Greater Bemidji Board done. |
| IPC, AIRC library connections with Acad. Affairs | II.4.2 | Ongoing | Provost, VP IEL, VP SDE | In process. University Commons model being considered for library. Collaboration between VPAA and VPSDE ongoing. |
| Faculty Lines | Appendix | Ongoing | Deans' Council, Cabinet | Added 6 new probationary lines fall 2013 and 6 new fixed-term lines for 80/20 programs. |
| Course evaluation | 11.4.7 | Fall 2015 | Deans’ Council | Draft proposal taken to BSUFA meet and confer February 2014 |